## PRL
82.5
[7 empty] | Must Have | 157.5 | 78.75 | 58.33%
[7 empty] | Should Have | 55.5 | 27.75 | 20.56%
[7 empty] | Could Have | 58 | 29 | 21.48%
[7 empty] | Won't Have | 122 | 61 | 45.19%
ID | Task | Relating to | PP | MoSCoW (Inc 1) | Time Box | Notes |  | Timebox 1 | Timebox 2
1 | Complete navigation | Overall | 1 | Must Have | Timebox 1 |  | Must Have | 91.55% | 56.34%
3.3 | Content Design and Structure | Overall | 20 | Must Have | Timebox 1 |  | Should Have | 7.042% | 45.07%
7 | Security review | Overall | 20 | Must Have | Timebox 2 |  |  | 98.59% | 101.4%
8.1 | Remove status (dropdown) | New Request Carousel | 0.5 | Must Have | Timebox 1
8.3 | Data validation | New Request Carousel | 8 | Must Have | Timebox 1
9.1 | Agree and complete carousel structure for tasks | My Tasks / Team's Tasks | 5 | Must Have | Timebox 1
9.2 | Agree and complete carousel structure for projects | My Projects | 3 | Must Have | Timebox 1
9.5 | Agree final status list | Task / Project Carousel | 2 | Must Have | Timebox 1
10 | Agree final milestone list | Overall | 2 | Must Have | Timebox 1
11 | Relocate new request button into 'My Requests' tab | My Requests | 1 | Must Have | Timebox 1
14 | Build profiles / authorisation levels | Overall | 13 | Must Have | Timebox 1
15 | Organise platform / host | Overall | 40 | Must Have | Timebox 2
16 | Dynamic buttons / tab visibility for each profile | Overall | 20 | Must Have | Timebox 1
22 | Audit logs (including link/button on all carousels) | Overall | 20 | Must Have | Timebox 1
23 | Clickability of rows | Everything minus Analytics | 2 | Must Have | Timebox 1
2 | Name the portal | Overall | 1 | Should Have | Timebox 1
3.1 | Agree colour scheme / overall design | Overall | 3 | Should Have | Timebox 1
3.2 | Implement colour scheme / overall design | Overall | 40 | Should Have | Timebox 2
4.1 | Build List of KPI's | Analytics | 10 | Won't Have
4.2 | Build in visualisations | Analytics | 20 | Won't Have
4.3 | Exportable data (automatable) | Analytics | 10 | Won't Have
27 ** | Profile Based Planning Forecast | Overall | ?? | Won't Have
5.1 | Push emails | New Request Carousel / Subscriptions | 20 | Could Have
5.2 | Subscriptions | Subscriptions | 8 | Won't Have
5.3 | Visual notifications | Overall | 3 | Should Have | Timebox 1
8.2 | Quick win option (tick box) | New Request Carousel | 0.5 | Should Have | Timebox 1
9.3 | Attachments, including sections for gov docs (e.g. PRL, SAD, DAD) | Task / Project Carousel | 20 | Could Have
9.4 | Notes / comments (including notes history section bottom of form) | Task / Project Carousel | 5 | Should Have | Timebox 2
12 | Build reports register | Reports Register | 5 | Won't Have
13 | Build data dictionary | Data Dictionary | ? | Won't Have
19 | Build in filters / search bar | Overall | 5 | Could Have
19.1 | Build in filters / search bar | Analytics | 0.5 | Could Have
19.2 | Build in filters / search bar | My Requests | 0.5 | Could Have
19.3 | Build in filters / search bar | Subscriptions | 0.5 | Could Have
19.4 | Build in filters / search bar | My Tasks | 0.5 | Could Have
19.5 | Build in filters / search bar | Team Tasks | 0.5 | Could Have
19.6 | Build in filters / search bar | My Projects | 0.5 | Could Have
19.7 | Build in filters / search bar | Reports Register | 0.5 | Could Have
19.8 | Build in filters / search bar | Data Dictionary | 0.5 | Could Have
19.9 | Build in filters / search bar | Admin | 0.5 | Could Have
19.1 | Build in filters / search bar | All Projects | 0.5 | Could Have
20 | Automated keyword lookup on new request for duplicate tasks | New Request Carousel | 8 | Could Have
21 | Kanban board | All Projects | 40 | Won't Have
24 | Outlook interfacing (including dev time calendar invites) | Overall | 20 | Won't Have
26.1 | Modify Profiles | Admin | 3 | Should Have | Timebox 2
26.2 | Modify Email Templates | Admin | 3 | Won't Have
26.3 | Modify Subscriptions | Admin | 3 | Won't Have
26.4 | Modify Approvals | Admin | 3 | Won't Have

## Tabs
Tab | Access | Actions Available on Tab | Actions Available on Form | Notes
My Requests | Everyone | New Request View Request [Filters - 'Open' by default] | Submit Request Cancel Handover Request Cancel Request | This is where you can view any request that you've previously submitted (default is only open requests visible until filter is removed). You can also create new requests here and cancel existing requests (cancels have to be approved by manager of development OR manager of request if development has not yet started). When creating a new task, the system should automatically scan keywords against the 'All Projects' list and prompt the customer for potential duplication (e.g. did you mean this?).
My Tasks | Everyone | Update Task [Filters - 'Open' by default] | Submit Request (Rollback to Cust) Approve Request (M1) Reject Request (M1) Allocate Developer (M2) Complete Solution (M3) Approve Solution (M4/5/6/7) Amend Project Status Reallocate Task Rollback Project | This is where you can view any tasks that you have been allocated, past or present. By default this is only open tasks. This is the main place to manage progression of a project, including for the customer (the customer may need to provide further information to the request here if rolled back / approve the final solution once complete). The different milestone status of the project (see Drawio flow chart for milestones) dictate what actions are available to the user - this will also be profile managed. You can reallocate tasks to others (e.g. for cover), but this will need some form of validation applied to ensure they're going to the right people.
My Projects | Team | View Project [Filters - 'Open' by default] | [As above, if task is with user] | This is where you can view any projects that you have worked on, past or present (at some point had a task relating / contributing to the project). By default, this shows only open projects. You are able to see projects in your queue that you don't currently have a task for, if you have worked on it at some point. If the task is assigned to you on the project, you can access the actions exactly the same as on the 'My Tasks' tab.
My Team's Tasks | Manager / Specialist | View Task [Filters - 'Open' by default] | Amend Project Status Reallocate Task | This is where managers (including senior devs) can view all tasks currently open within the team (e.g. Leon, Mark N and Ant would see Innovations - Mark H would see the manager's / specialists). Here we can over-rule and reallocate tasks for escalation and contingency purposes. You can also view closed tasks within the team, but these are hidden by default.
All Projects | Everyone | View Project [Filters - 'Open' by default] | [As above, if x] | This will show all projects, regardless of ownership. By default, there is a filter applied to only show open projects, but you can remove this (as with other tabs) to view closed projects too. Similar to above, if you own the open task on an open project, you'll be presented with the same actions as within the 'My Tasks' tab, or if you're a manager (or specialist) of the person who owns the open task, you have the actions available from the 'My Team's Tasks' tab. Customers can also view this tab, but wouldn't be granted any actions - this would be view only for awareness and engagement purposes. Includes Kanban board option.
Data Dictionary | Everyone | TBC | TBC | Shows all tables and descriptions of the data within Oracle SQL (Possibly GCP)
Reports Register | Everyone | TBC | TBC | Shows all our owned reports and where to find them
Subscriptions | Everyone | TBC | TBC | Allows the end-user to request subscriptions to reporting updates
Analytics | Team | TBC | TBC | This can show stats such as week on week turnaround time for requests, health indicators for workload across the team etc.
Admin | Manager / Specialist | TBC | TBC | Allows Manager/Specialist to amend a predetermined set of rules

## Data Points
Data Point | Description | Example | Type | My Requests | My Tasks | My Projects | My Team's Tasks | All Projects | Subscriptions | Admin
REQUEST_ID | Unique identifier for each request | R1 | Generated
PROJECT_ID | Unique identifier for each project | P1 | Generated
TASK_ID | Unique identifier for each task | T1 | Generated
INCREMENT_ID | Unique identifier for each request | I1 | Generated
TIMEBOX_ID | Unique identifier for each project | B1 | Generated
CUSTOMER_EIN |  |  | Number(9)
SPONSOR_EIN |  |  | Number(9)
REQUEST_NAME | Request Name | A new Ethernet Repair tracker | Free text
REQUEST_DESC | Request Description | A new app to accurately track our repair progress on Ethernet, including weekly trends, dwell times and geographical success. | Free text
PROGRAMME
CATEGORY
RATIONALE
REQUEST_URGENCY
REQUEST_ATTACHMENT
STATUS
PROJECT_NAME | Project Name | Ethernet Repair App | Free text
PRIORITY_SCORE | Priority score using RICE
INCREMENT_NUM
TIMEBOX_NUM
MILESTONE
MILESTONE_DESC
MILESTONE_DT
REQUESTER_EIN |  |  | Generated(21c)
REQUESTER_NAME |  |  | Generated
REQUESTER_EMAIL |  |  | Generated
CUSTOMER_NAME |  |  | Generated
CUSTOMER_EMAIL |  |  | Generated
FACILITATOR_EIN |  |  | Number(9)
FACILITATOR_NAME |  |  | Generated
FACILITATOR_EMAIL |  |  | Generated
DEVELOPER_EIN |  |  | Number(9)
DEVELOPER_NAME |  |  | Generated
DEVELOPER_EMAIL |  |  | Generated
FACILITATOR_MGR_EIN |  |  | Number(9)
FACILITATOR_MGR_NAME |  |  | Generated
FACILITATOR_MGR_EMAIL |  |  | Generated
DEVELOPER_MGR_EIN |  |  | Number(9)
DEVELOPER_MGR_NAME |  |  | Generated
DEVELOPER_MGR_EMAIL |  |  | Generated
PEER_REVIEWER_EIN |  |  | Number(9)
PEER_REVIEWER_NAME |  |  | Generated
PEER_REVIEWER_EMAIL |  |  | Generated
SPONSOR_NAME |  |  | Generated
SPONSOR_EMAIL |  |  | Generated
P_OPEN
P_CLOSE
P_PROG
P_TYPE
PRIORITY
RATIONALE
(Subscription stuff?)
(Logging stuff?)
WIREFRAME
COMMENTS
REQUIREMENTS (list)
P_PLATFORM

## Data Dictionary
Visibility
Count | PK | FK | Column | Table | Data Type | Length | My Requests Page | My Tasks Page | My Projects Page | My Team's Tasks Page | All Projects Page | Subscriptions Page | My Requests Modal | My Tasks Modal | My Projects Modal | My Team's Tasks Modal | All Projects Modal
1 | Y |  | EVENT_ID | EVENTS
2 |  |  | EVENT_TIME | EVENTS
3 |  |  | EVENT_EIN | EVENTS
4 |  |  | EVENT_AREA | EVENTS
5 |  |  | EVENT_LEVEL | EVENTS
6 |  | Y | REQUEST_ID | EVENTS
7 | Y |  | SUB_ID | SUBSCRIPTIONS | [7 empty] | Y
8 |  |  | SUB_EVENT | SUBSCRIPTIONS | [7 empty] | Y
9 |  |  | SUB_SCHEDULE | SUBSCRIPTIONS | [7 empty] | Y
10 |  |  | SUB_TYPE | SUBSCRIPTIONS | [7 empty] | Y
11 |  | Y | REQUEST_ID | SUBSCRIPTIONS | [7 empty] | Y
12 | Y |  | REQUEST_ID | REQUESTS |  |  | Y
13 |  | Y | REQUEST_EIN | REQUESTS
14 |  | Y | CUST_EIN | REQUESTS
15 |  | Y | SPONSOR_EIN | REQUESTS
16 |  |  | REQUEST_NAME | REQUESTS |  |  | Y
17 |  |  | REQUEST_DESC | REQUESTS
18 |  |  | PROG | REQUESTS |  |  | Y | Y | Y | Y | Y
19 |  |  | CATEGORY | REQUESTS |  |  | Y | Y | Y | Y | Y
20 |  |  | RATIONALE | REQUESTS
21 |  |  | AUDIENCE | REQUESTS
22 |  |  | URGENCY | REQUESTS |  |  | Y
23 |  |  | REQUEST_STATUS | REQUESTS |  |  | Y (ish)
24 | Y |  | EIN | PEOPLE
25 |  |  | FIRST_NAME | PEOPLE
26 |  |  | LAST_NAME | PEOPLE
27 |  |  | EMAIL | PEOPLE
28 |  |  | OUC | PEOPLE
29 |  |  | MGR_EIN | PEOPLE
30 |  |  | MGR_FIRST_NAME | PEOPLE
31 |  |  | MGR_LAST_NAME | PEOPLE
32 |  |  | MGR_EMAIL | PEOPLE
33 |  |  | MGR_OUC | PEOPLE
34 |  | Y | REQUEST_ID | PROJECT_MAPPING
35 |  | Y | PROJECT_ID | PROJECT_MAPPING | [7 empty] | Y
36 |  | Y | TASK_ID | TASK_MAPPING
37 |  | Y | REQUEST_ID | TASK_MAPPING
38 |  | Y | PROJECT_ID | TASK_MAPPING |  |  |  | Y |  | Y
39 | Y |  | TASK_ID | TASKS |  |  |  | Y |  | Y
40 |  |  | TASK_NAME | TASKS |  |  |  | Y |  | Y
41 |  | Y | OWNER_EIN | TASKS
42 |  | Y | DELEGATE_EIN | TASKS
43 |  |  | ROLLBACK_REASON | TASKS
44 |  |  | TASK_STATUS | TASKS |  |  |  | Y |  | Y
45 |  |  | TASK_OPEN_DT | TASKS
46 |  |  | TASK_CLOSE_DT | TASKS
47 | Y |  | COMMENT_ID | COMMENTS
48 |  |  | COMMENT | COMMENTS
49 |  |  | COMMENT_DT | COMMENTS
50 |  | Y | COMMENT_EIN | COMMENTS
51 | Y |  | PROJECT_ID | PROJECTS |  |  |  |  | Y |  | Y
52 |  |  | HOLD_REASON | PROJECTS
53 |  |  | STATUS | PROJECTS |  |  | Y (ish) | Y | Y | Y | Y
54 |  |  | QUICK_WIN | PROJECTS
55 |  |  | PROJECT_NAME | PROJECTS |  |  |  | Y | Y | Y | Y
56 |  |  | PRIORITY_SCORE | PROJECTS |  |  |  | Y | Y | Y | Y
57 |  |  | PLATFORM | PROJECTS |  |  |  |  | Y |  | Y
58 |  |  | WIREFRAME | PROJECTS
59 |  |  | MOSCOW | PROJECTS
60 |  |  | USER_STORY | PROJECTS
61 |  |  | WIREFRAME_SKIP | PROJECTS
62 |  |  | MOSCOW_SKIP | PROJECTS
63 |  |  | USER_STORY_SKIP | PROJECTS
64 |  |  | PROJECT_ECD | PROJECTS |  |  |  |  | Y |  | Y
65 |  |  | MILESTONE | PROJECTS |  |  | Y | Y | Y | Y | Y
66 |  | Y | TASK_ID | ATTACHMENTS
67 |  |  | ATTACHMENT | ATTACHMENTS
68 |  | Y | TASK_ID | COMMENT_MAPPING
69 |  | Y | REQUEST_ID | COMMENT_MAPPING
70 |  | Y | PROJECT_ID | COMMENT_MAPPING
71 |  | Y | COMMENT_ID | COMMENT_MAPPING
72 | Y |  | INCREMENT_ID | INCREMENTS
73 |  | Y | PROJECT_ID | INCREMENTS
74 |  |  | INCREMENT_ECD | INCREMENTS
75 | Y |  | TIMEBOX_ID | TIMEBOXES
76 |  | Y | INCREMENT_ID | TIMEBOXES
77 |  |  | TIMEBOX_ECD | TIMEBOXES
78 |  |  | TIMEBOX_LENGTH | TIMEBOXES